| Membership category | Action | 2005 | 2006 | 2007 | 2008 |
| --- | --- | --- | --- | --- | --- |
| General | 1. CERL Website: restructure and redesign | New ‘Provenance Information’ section designed (September) Specification for new website | Create new ‘Publications’ section Add PDF files for CERL Papers I–3, HPB leaflets etc. Appoint design firm | Review HPB section in the light of the new contract Develop further features | Review the new design |
|  | 2. CERL Literature pack | Revised and expanded | Revise annually; and add information sheets for new initiatives | Revise annually | Revise annually |
|  | 3. CERL Leaflets |
|  | 3.1 General leaflet | Written, designed and printed (July) Copies sent to IFLA Pre-Conference and IFLA Conference (August) Copies distributed to LIBER libraries in LIBER mailing (August) To be updated and put on website | Revise annually and plan distribution to IFLA and other major events | Revise annually and distribute | Revise annually and distribute |
|  | 3.2. Leaflet for Antiquarian booksellers | Designed (July/August) for printing on office printer Sent out to 40 US booksellers | Revise and prepare distribution plans | Revise and prepare distribution plans | Revise and prepare distribution plans |
|  | 3.3. Publicity leaflet for CERL Papers V | Prepared (August) for printing on office printer Distributed at Provenance conference, Cambridge (September) Insert arranged for the Bibliographical Society’s journal (December) | Find opportunities to distribute Prepare version for CERL Papers VI | Find opportunities to distribute Prepare version for CERL Papers VII | Find opportunities to distribute Prepare version for CERL Papers VIII |
|  | 3.4 HPB leaflets | Distributed at 3 international conferences and 4 national conferences in 5 number of countries. Put PDF files on new section of website | Update and reprint as necessary Take forward Spanish and German versions | Update and reprint as necessary Investigate other language versions | Update and reprint as necessary Investigate other language versions |
|  | 3.5. Other leaflets |  | Design, produce and distribute: CERL Manuscript Service CERL Thesaurus Mount on website |  |  |
|  | 4. Workshops and seminars |
|  | 4.1. CERL Annual Seminar | ‘Many into one’, Biblioteca Nazionale Centrale, Rome, 11 November 2005 Policy document on Annual Seminars prepared. | Organise Seminar at National Széchényi Library, Budapest, 11 November 2006 (theme to be announced ) Select venue and theme for following year | Organise Seminar for current year Select venue and theme for following year Review policy document on Annual Seminars | Organise Seminar for current year Select venue and theme for following year |
|  | 4.2. CERL Papers series | Edit and publish previous year’s Annual Seminar papers in time for current year’s Seminar. Publicise sales of current and past CERL Papers |
|  | 4.3 CERL Workshops | Zagreb: March 2005 | Estonia; Lyon | To be arranged | To be arranged |
|  | 4.4 Seminars and Conferences: CERL participation | IFLA Pre-Conference, Copenhagen Cambridge Tours | Sharp, The Hague | To be arranged | To be arranged |
|  | 5. Membership enquiries | Follow up all membership enquiries (literature; offer of HPB trial password; workshop) |
| Full and Group Membership | 6. Country/region promotion * An asterisk indicates countries which have not yet contributed records to the HBP. | Latvia * France Italy UK Norway * | Austria * Estonia * Germany Hungary Spain Switzerland * Follow up and extend previous contacts | Australia * Canada * New Zealand * Poland Slovenia USA * Follow up and extend previous contacts | Japan Follow up and extend previous contacts |
|  |  |  | Discuss North American membership arrangements with RLG | Implement post-2006 contract arrangements on membership |  |
|  | 7. Group Membership | New arrangements posted on website and in CERL literature | Promote revised form of Group Membership | Seek to create special Group Memberships |  |
|  | 8. Special Members |
|  | 8.1. Antiquarian booksellers | List of US book trade prepared. Leaflets and letters sent out (September) Contact with ABA (UK) Contacts with ILAB | Follow-up USA Prepare list for UK, France, send out letters Follow up ILAB | Follow up UK, France Prepare list for Germany, Italy | Prepare list for Belgium, Netherlands Follow up |
|  | 8.2. Auction houses |  | Identify potential targets | Follow up |  |
|  | 8.3. Centres for the Book; Museums |  | Prepare special leaflet Draw up lists and send leaflets | Follow up |  |
|  | 8.4. National non-publicly funded bodies |  | National Trust and National Trust for Scotland (UK) | Follow up |  |
|  | 8.5. Private historic libraries | Contact made in UK | Follow up; look for new contacts |  |  |
| Other arrangements | 9. Special arrangements To be negotiated with Directors | ABINIA: negotiations prepared for AGM | Follow up ABINIA. Investigate North Africa | Follow up |  |
|  | 10. Individual access to HPB For private individuals without institutional access | Discuss access mechanisms with RLG | Devise guidelines and implement service | Publicise service |  |

# DJS, 25 October 2005